## Gantt Chart
CompassCHW — Project Gantt Chart
Community Health Worker Marketplace • 1 dev + Claude Code • github.com/Compasschw/Compass • joincompasschw.com • Updated April 15, 2026
[6 empty] | Week of Apr 07 | [5 empty] | Week of Apr 13 | [6 empty] | Week of Apr 20 | [6 empty] | Week of Apr 27
Phase | Task / Feature | Start | End | Days | Status | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2
Phase 0: Project Init & Original Build (Apr 7–9)
| Initial commit & repo creation | 2026-04-07 | 2026-04-07 | 1 | Done
| Platform init — web app, iOS preview, docs, infra planning | 2026-04-07 | 2026-04-07 | 1 | Done
| Vercel SPA routing config & gitignore | 2026-04-07 | 2026-04-07 | 1 | Done
| Landing page design spec + implementation plan | 2026-04-07 | 2026-04-08 | 2 | Done
| Original landing page sections (NavBar → Footer, 10 components) | 2026-04-08 | 2026-04-08 | 1 | Done
| FastAPI backend scaffold + Pydantic schemas + Alembic | 2026-04-08 | 2026-04-08 | 1 | Done
| Frontend API layer (TanStack Query) + comprehensive audit fixes | 2026-04-08 | 2026-04-08 | 1 | Done
| Auth hardening — .env config, token expiry, email validation | 2026-04-09 | 2026-04-09 | 1 | Done
| Backend hardening — DB rollback, Decimal types, state machine, billing cap | 2026-04-09 | 2026-04-09 | 1 | Done
| Shared components — LoadingSkeleton, EmptyState, format utils | 2026-04-09 | 2026-04-09 | 1 | Done
| Waitlist API endpoint + wire frontend forms | 2026-04-09 | 2026-04-09 | 1 | Done
| AWS production deployment prep + CSP/proxy fixes (7 commits) | 2026-04-09 | 2026-04-09 | 1 | Done
| Wire auth to real backend API + backend tests | 2026-04-09 | 2026-04-09 | 1 | Done
| Rate limiting, CI, wire CHWRequests + earnings + browse endpoints | 2026-04-10 | 2026-04-10 | 1 | Done
| Golden path — end-to-end session lifecycle with real API | 2026-04-10 | 2026-04-10 | 1 | Done
| Auto-unit billing, in-session chat UI, comms research | 2026-04-10 | 2026-04-10 | 1 | Done
| Communication layer — Vonage adapter + security audit fixes | 2026-04-10 | 2026-04-10 | 1 | Done
Phase 1: Lovable Landing Page Integration (Apr 10–11)
| Discovered compass-next-chapter Lovable repo, cloned into codebase | 2026-04-10 | 2026-04-10 | 1 | Done
| Copied landing components (Hero, Services, HowItWorks, ForCHWs, MobileFirst, CTA, Footer) | 2026-04-10 | 2026-04-10 | 1 | Done
| Wired waitlist form to FastAPI backend (POST /api/v1/waitlist/ + localStorage fallback) | 2026-04-10 | 2026-04-10 | 1 | Done
| Added framer-motion, class-variance-authority, clsx, tailwind-merge, @radix-ui dependencies | 2026-04-10 | 2026-04-10 | 1 | Done
| Added @/ path alias to vite.config.ts and tsconfig.app.json | 2026-04-10 | 2026-04-10 | 1 | Done
| Merged Tailwind v4 theme with Lovable design tokens (CSS vars, fonts, shadows, gradients) | 2026-04-10 | 2026-04-10 | 1 | Done
| Updated App.tsx routing — new landing at /, /waitlist route, preserved all existing routes | 2026-04-10 | 2026-04-10 | 1 | Done
| Created PR #2, pushed to feat/new-landing-page branch | 2026-04-11 | 2026-04-11 | 1 | Done
Phase 2: Full Web Frontend UI Migration to Lovable Design (Apr 11–12)
| Replaced Sidebar + BottomNav with shadcn collapsible sidebar (DashboardSidebar, DashboardLayout) | 2026-04-11 | 2026-04-11 | 1 | Done
| Restyled LoginPage and RegisterPage — Lovable 2-column split, gradient bar, Framer Motion | 2026-04-11 | 2026-04-11 | 1 | Done
| Restyled CHWDashboard and MemberHome — stat card pattern, card lists, staggered animations | 2026-04-11 | 2026-04-11 | 1 | Done
| Restyled CHWSessions (1,477 lines) and MemberSessions (612 lines) — CSS-only, logic preserved | 2026-04-11 | 2026-04-11 | 1 | Done
| Restyled CHWEarnings (bar chart, transaction cards) + CHWRequests (summary stats, filter tabs) | 2026-04-11 | 2026-04-11 | 1 | Done
| Restyled CHWProfile (1,151 lines) + MemberProfile (1,148 lines) — gradient header, info cards | 2026-04-11 | 2026-04-11 | 1 | Done
| Restyled CHWCalendar, MemberCalendar, MemberFind, MemberRoadmap, Onboarding screens | 2026-04-11 | 2026-04-11 | 1 | Done
| Updated Badge, VerticalIcon, StatCard, ErrorBoundary, LoadingSkeleton, WaitlistAdmin | 2026-04-11 | 2026-04-11 | 1 | Done
| Fixed CSS @import order, added container utility for Tailwind v4, added /auth route | 2026-04-12 | 2026-04-12 | 1 | Done
| Added @utility definitions for text-display-xl/lg/md/sm, text-body-lg/md/sm, text-label | 2026-04-12 | 2026-04-12 | 1 | Done
| Wired all CTA buttons to /auth (Hero, CTASection, ForCHWs, MobileFirst) | 2026-04-12 | 2026-04-12 | 1 | Done
| Rewrote LoginPage to match Lovable Auth.tsx (Google/Apple social buttons, sign-up/sign-in toggle) | 2026-04-12 | 2026-04-12 | 1 | Done
Phase 3: React Native Full Rebuild (Apr 13–14)
| Created Expo project (CompassCHW-Mobile) with blank-typescript template | 2026-04-13 | 2026-04-13 | 1 | Done
| Installed React Navigation, AsyncStorage, SecureStore, Reanimated, Gesture Handler, Lucide, SVG | 2026-04-13 | 2026-04-13 | 1 | Done
| Built core architecture — theme, API client (JWT + auto-refresh via SecureStore), auth context, mock data | 2026-04-13 | 2026-04-13 | 1 | Done
| Built navigation — AppNavigator (auth-gated), CHWTabNavigator (6 tabs), MemberTabNavigator (6 tabs) | 2026-04-13 | 2026-04-13 | 1 | Done
| Built all 6 CHW screens — Dashboard, Requests, Sessions, Earnings, Profile, Calendar | 2026-04-13 | 2026-04-13 | 1 | Done
| Built all 6 Member screens — Home, FindCHW, Sessions, Roadmap, Profile, Calendar | 2026-04-13 | 2026-04-13 | 1 | Done
| Built auth screens — LoginScreen (sign-in/sign-up, Google/Apple SVG, demo fallback), WaitlistScreen | 2026-04-13 | 2026-04-13 | 1 | Done
| Created Compasschw/CompassCHW-Native GitHub repo, pushed initial codebase | 2026-04-13 | 2026-04-13 | 1 | Done
| Built session doc modal (Z-codes, procedure codes, units stepper, goals, resources, follow-up) | 2026-04-13 | 2026-04-13 | 1 | Done
| Built session chat (FlatList, sent/received bubbles, timestamps) + live timer + consent flow | 2026-04-13 | 2026-04-13 | 1 | Done
| Built CHW onboarding (4-step) + Member onboarding (4-step) | 2026-04-13 | 2026-04-13 | 1 | Done
| Profile editing, earnings scenarios, rewards catalog, request summary stats | 2026-04-13 | 2026-04-13 | 1 | Done
| API modules (conversations, credentials, matching, upload) + shared components + legal screen | 2026-04-13 | 2026-04-13 | 1 | Done
| Milestone: 42 files, 19,356 lines of TypeScript | 2026-04-14 | 2026-04-14 | 1 | Done
Phase 4: Lovable Design System → React Native (Apr 14–15)
| Installed DM Sans + Plus Jakarta Sans via @expo-google-fonts, updated App.tsx with useFonts | 2026-04-14 | 2026-04-14 | 1 | Done
| Updated theme — exact Lovable HSL colors, Platform-specific shadows, spacing scale, radii | 2026-04-14 | 2026-04-14 | 1 | Done
| Restyled auth screens + onboarding to match Lovable (card patterns, gradient bars, input styling) | 2026-04-14 | 2026-04-14 | 1 | Done
| Restyled all 12 dashboard screens to match Lovable (cards, badges, fonts, stat patterns, gradients) | 2026-04-14 | 2026-04-14 | 1 | Done
| Updated tab bar styling (active tint, font, shadow) | 2026-04-14 | 2026-04-14 | 1 | Done
| Added mock login fallback (loginMock in AuthContext) for offline demo | 2026-04-14 | 2026-04-14 | 1 | Done
| Built responsive landing page — 2-column hero with CHW/Member toggle, floating stats card | 2026-04-14 | 2026-04-14 | 1 | Done
| Built InfiniteSlider client section + Services section (6-card grid) | 2026-04-14 | 2026-04-14 | 1 | Done
| Built HowItWorks, ForCHWs, MobileFirst, CTA overlay, 4-column Footer sections | 2026-04-14 | 2026-04-14 | 1 | Done
| Added scrollable nav links with measureLayout scroll-to-section | 2026-04-14 | 2026-04-14 | 1 | Done
| Matched waitlist page to Lovable (2-column desktop, dropdown role selector, top navbar) | 2026-04-15 | 2026-04-15 | 1 | Done
| Added compass icon to logo, fixed headline sizes, removed secondary CTA buttons | 2026-04-15 | 2026-04-15 | 1 | Done
| Added Transportation Assistance as 6th service vertical | 2026-04-15 | 2026-04-15 | 1 | Done
| Updated hero stat to '3M+ Medi-Cal Members In Need', removed stats bar from services | 2026-04-15 | 2026-04-15 | 1 | Done
| Fixed CTA image coverage, reduced section spacing by 50%, removed demo login buttons | 2026-04-15 | 2026-04-15 | 1 | Done
Phase 5: Backend Wiring + Production Deployment (Apr 15)
| Installed @tanstack/react-query, wrapped app in QueryClientProvider | 2026-04-15 | 2026-04-15 | 1 | Done
| Created useApiQueries.ts — 12 query hooks + 9 mutation hooks with snake/camelCase auto-transform | 2026-04-15 | 2026-04-15 | 1 | Done
| Created caseTransform.ts (transformKeys, toSnakeCase) + ErrorState shared component | 2026-04-15 | 2026-04-15 | 1 | Done
| Wired 6 CHW screens to live API (replaced all mock imports with React Query hooks) | 2026-04-15 | 2026-04-15 | 1 | Done
| Wired 5 Member screens to live API (MemberRoadmap stays mock — no backend goals endpoint) | 2026-04-15 | 2026-04-15 | 1 | Done
| Updated backend CORS to allow Expo dev ports (8082, 19006, 8081) | 2026-04-15 | 2026-04-15 | 1 | Done
| Created .env with EXPO_PUBLIC_API_URL, copied native/ into monorepo, renamed web/ to web-legacy/ | 2026-04-15 | 2026-04-15 | 1 | Done
| Added vercel.json with Expo web build config, API proxy, security headers | 2026-04-15 | 2026-04-15 | 1 | Done
| Created PR #3, merged to main, redeployed to joincompasschw.com via Vercel | 2026-04-15 | 2026-04-15 | 1 | Done
| Verified live waitlist submissions recording to PostgreSQL database | 2026-04-15 | 2026-04-15 | 1 | Done
Planned / Not Yet Built
| Google/Apple OAuth integration (buttons exist, show 'coming soon') | 2026-04-16 | 2026-04-22 | 7 | Planned
| React Native Maps for CHW discovery (needs Google Maps API key + native config) | 2026-04-16 | 2026-04-22 | 7 | Planned
| Push notifications (not implemented) | 2026-04-18 | 2026-04-24 | 7 | Planned
| Camera/photo upload for profiles and credentials (expo-image-picker installed, not wired) | 2026-04-18 | 2026-04-23 | 6 | Planned
| Member goals/roadmap backend API endpoint (screen stays on mock data) | 2026-04-20 | 2026-04-25 | 6 | Planned
| Rewards redemption backend API endpoint (stays on mock data) | 2026-04-20 | 2026-04-25 | 6 | Planned
| Full credential upload and verification flow (placeholder UI only) | 2026-04-22 | 2026-04-28 | 7 | Planned
| iOS/Android App Store builds via EAS Build | 2026-04-24 | 2026-04-30 | 7 | Planned
| PWA service worker for offline support | 2026-04-26 | 2026-05-02 | 7 | Planned
| Mobile hamburger menu for nav links | 2026-04-16 | 2026-04-18 | 3 | Planned
Phase Legend
Project Init & Original Build
Lovable Landing Page Integration
Full Web Frontend UI Migration
React Native Full Rebuild
Lovable Design System → React Native
Backend Wiring + Production Deployment
Planned / Not Yet Built

## Summary
CompassCHW Project Summary
Phase | Start Date | End Date | # Tasks | Status
Phase 0: Project Init & Original Build (Apr 7–9) | 2026-04-07 | 2026-04-10 | 17 | Complete
Phase 1: Lovable Landing Page Integration (Apr 10–11) | 2026-04-10 | 2026-04-11 | 8 | Complete
Phase 2: Full Web Frontend UI Migration to Lovable Design (Apr 11–12) | 2026-04-11 | 2026-04-12 | 12 | Complete
Phase 3: React Native Full Rebuild (Apr 13–14) | 2026-04-13 | 2026-04-14 | 14 | Complete
Phase 4: Lovable Design System → React Native (Apr 14–15) | 2026-04-14 | 2026-04-15 | 15 | Complete
Phase 5: Backend Wiring + Production Deployment (Apr 15) | 2026-04-15 | 2026-04-15 | 10 | Complete
Planned / Not Yet Built | 2026-04-16 | 2026-05-02 | 10 | Planned
TOTAL TASKS |  |  | 86
Project Stats
Project Timeline | Apr 7 – Apr 15, 2026 (9 days)
Team | 1 developer + Claude Code AI pair programming
Web Frontend | React 19 + TypeScript 5.9 + Vite + Tailwind CSS 4
Mobile | Expo (React Native) — 42 files, 19,356 lines TypeScript
Backend | Python/FastAPI + PostgreSQL + AWS
Deployment | Vercel (web) • joincompasschw.com
Repo | github.com/Compasschw/Compass